## Instructions
Tab Reference | Comments | ID Key | Description
Cost_Estimate_Summary | Based on all activities within the Corridor selected | PHubX | Piopiotahi Visitor Hub
| Visitor Hub established in Te Anau | PDelX | Piopiotahi Delta Experience and Surrounding Areas
| Captial Costs for establishment of the options selected | PDWX | Piopiotahi Deep Water Basin
| All columns use vLookup to Cost_Estimates tab referencing the ID | PFWX | Piopiotahi Fresh Water Basin
DO NOT make changes in this TAB
Cost Estimates | Cost estimate build up for elements within the Summary Tables | CKFX | Corridor Knobs Flat Experience
| Built up on Base Rates (refer Reference Costings Tab), with uplift for location, uncertainty of scope, Contractor Contingencies, procurement, professional fees and contingency | CCEX | Corridor Experience - away from Principal Nodes
| % uplift provided for certain elements and can be adjusted. These feed through the subsequent sheets | CTHX | Corridor Super Track Head
Estimate of Build Start and Completion dates provided for the activities
Reference Costings | Base cost estimates for elements of work including supporting source. | TAVX | Te Anau Visitor Hub Experience
| Where a source is not available then the items is identified as an estimate of works. This may be due to uncertainty of the extent and scope of the option selected/costed | TABX | Te Anau Bus Services and Parking
Orange cells show where costs are estimated and source is not readily available to align with the option.
Assumptions | Collation of Assumptions used (to be added to as required)
XXXX_30112020 | Documentation of base assessments (where possible) for measurements used in the Cost Estimate Tab
RELEASED BY THE MINISTER OF CONSERVATION

## Cost_Estimate_Summary
[8 empty] | Baseline Year | 2022
ID | Location | CBA_Reference | Description | Comment | Unit | Quantity_Max | Cost_Estimate | Year_Established | Year_Established | Construction_Duration | Completion | Development_Comments | Life_Expectancy | OPEX_(Annual) | OPEX_Comments
PHub1 | Piopiotahi | Visitor Hub | Deconstruction - Existing Hub | Removal of structures in the central hub to make way for Visitor Experience, Accommodation and Marine Centre | m2 | 6125 | 1844000 | 0 | 2022 | 1 | 2023
PHub2 | Piopiotahi | Visitor Hub | Visitor Experience Hub - Piopiotahi | Facility developed to act as the focal point for the overall experience. Ticketing, interactive displays, information, services. Proposed adjacent to or including Marine Interpretive Centre. | m2 | 1800 | 21281000 | 0 | 2022 | 3 | 2025
PHub3 | Piopiotahi | Visitor Accomodation | Accomodation - Visitors | 100 bed accommodation targetting overnight stays, styled as a 3 Star Hotel, resilient to withstand extreme events and act as a refuge. | m2 | 1540 | 21120000
PHub4 | Piopiotahi | Staff Accomodation | Accomodation - Staff | 280-320 bed accommodation for staff, some single units and some shared rooms, resilient to withstand extreme events and act as a refuge. | m2 | 5100 | 43412000
PHub5 | Piopiotahi | Marine Centre | Marine Interpretive Centre - Piopiotahi | Facility developed to enhance visitor interaction. Touch pool, working lab, concourse/display area, back of house. Proposed adjacent to or part of Visitor Experience Hub. | m2 | 950 | 11233000
PHub6 | Piopiotahi | Staff Accomodation | Deconstruction - Staff Accommodation | Removal of Existing Housing and Staff accommodation in preparation for new infrastructure | m2 | 2850 | 858000 | 17 | 2039 | 1 | 2040 | As funding permits, requires new staff accommodation to be built
PHub7 | Piopiotahi | Arrival | Structures - Bus Stop - Piopiotahi arrival | Shelter / Refuge style of development acting as an arrival point for buses. Located a short distance from the Visitor Experience Hub | no. | 1 | 717000 | 0 | 2022 | 2 | 2024 | Base Option Design Yr 1, Construct Yr 2
PHub8 | Piopiotahi | Arrival | Structures - Covered Walkway - Piopiotahi arrival | Covered Walkway from Bus Arrival to Visitor Experience Hub | m | 170 | 650000 | 0 | 2022 | 2 | 2024 | Base Option Design Yr 1, Construct Yr 2
PHub9 | Piopiotahi | Road Realignment | Pavements - Realignment (Arrival) | New access into Piopiotahi established to bring the road (as a one way system) onto the alignment of the existing taxiway | m2 | 500 | 1348000 | 0 | 2022 | 3 | 2025 | Changed alignment for moving from two-way to one way for arrival access
PHub10 | Piopiotahi | Visitor Hub | Landscaping - Visitor Experience Hub - Piopiotahi | Water front development - to provide an enhanced enviroment including boardwalks, paving and landscaping surrounding the Visitor Hub | m2 | 10000 | 5192000
PHub11 | Piopiotahi | Visitor Hub | Deconstruction - Foreshore Carparking | Removal of existing carparking and pavement on the foreshore. Establish landscaping features / plantings in its place. | m2 | 5700 | 1606000 | 2 | 2024 | 1 | 2025 | Delayed start tied into visitor hub development
PHub12 | Piopiotahi | Wastewater | Services - Wastewater | Allowance for alteration of the existing wastewater network to accommodate the proposed developments within Piopiotahi. Upgrade to the current plant provided for with a higher rate and quality treatment to meet potential revised consent requirements |  |  | 2250000
PHub13 | Piopiotahi | Potable Water | Services - Potable Water | Allowance for alteration of the existing potable water network to accommodate the proposed developments within Piopiotahi. Increased storage (500m3) provided for. |  |  | 1603000
PHub14 | Piopiotahi | Power | Services - Power Supply | Allowance for replacement of the existing turbines and generators (and equipment) to accommodate the proposed developments within Piopiotahi. |  |  | 4993000
PHub15 | Piopiotahi | Visitor Hub | Piopiotahi Interpretation | Budget allowance for the establishment of interpretive materials throughout Piopiotahi (Signage, Displays, Services, incl. within the hub) | no. | 1 | 2000000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
PHub16 | Piopiotahi | Tracks & observation points | Piopiotahi Viewing Deck Walkway | Redevelopment of the existing walkway above the hub to including treetop canopy viewing platforms and a link to the Visitor Experience Hub |  |  | 1341000
PHub17 | Piopiotahi | Tracks & observation points | Walking Track - Accessible (Premium) | Wheelchair accessible Track (corridor access around the Visitor Hub not otherwise covered under the water front development). | m | 1000 | 977000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
PDel1 | Piopiotahi | Tracks & observation points | Deconstruction - Airport Runway | Removal of existing runway and pavement areas. Establish either landscaping features / planting or establish locations for helicopter landings in its place. | m2 | 16000 | 4506000 | 2 | 2024 | 1 | 2025 | Delayed start tied into visitor hub development
PDel2 | Piopiotahi | Tracks & observation points | Visitor Protection Refuges | Shelter / Refuge for hazards at key locations outside of the key structures (at Fresh Water Basin, Long Stay Parking, Deepwater Basin, Cleddau Delta). Double as infromation centres and potential observation points | no. | 4 | 2967000 | 0 | 2022 | 2 | 2024 | Base Option Design Yr 1, Construct Yr 2
PDel3 | Piopiotahi | Parking | Pavements - New Parking Area Sealed | Long stay parking and bus layover area. To be established within the footprint of the existing staff accommodation area. | m2 | 6000 | 3115000 | 0 | 2022 | 3 | 2025
PDel4 | Piopiotahi | Transport Terminal | Shuttles - Base of Operations | Area for the operation and maintenance of shuttles to take visitors from the hub to the terminal. Includes facilities for Bus driver resting, shuttle mainteance, charging and overnight housing |  |  | 4571000
PDel5 | Piopiotahi | Access Systems | Shuttles - Capital Investment | Purchase of shuttles to convey visitors from from Visitor Experience Hub to the ferry terminal. | no. | 12 | 10908000
PDel6 | Piopiotahi | Tracks & observation points | Delta Walking Track - Accessible | Accessible walking track developed through the Delta being mindful to minimise the physical footprint of the works. | m | 3600 | 2991000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
PDel7 | Piopiotahi | Tracks & observation points | Walking Track - Milford Lodge to Tutoko Bridge | Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards). Along SH94 alignment for 2000m and then 4000m upgrade alongside the Tutoko River | m | 4000 | 3323000 | 0 | 2022 | 3 | 2025
PDW1 | Piopiotahi | Commercial Fishing Port | Structures - Operations - Commercial port | Renewal of the existing building that houses the operations for the Commerical Port | m2 | 300 | 2413000 | 0 | 2022 | 3 | 2025 | Assumed Base Option Design Yr 1, Construct Yr 2/3
PDW2 | Piopiotahi | Commercial Fishing Port | Deepwater Basin Experience Hub | Focus for tourist activities within Deepwater basin. To include a pavilion, boardwalk, food stalls, pavement and landscaping |  |  | 2854000 | 0 | 2022 | 3 | 2025 | Assumed Base Option Design Yr 1, Construct Yr 2/3
PDW3 | Piopiotahi | Commercial Fishing Port | Kayak Landing point | Developed on the basis of a floating pontoon. This could be developed as a modified concrete boat ramp instead | m | 50 | 312000 | 0 | 2022 | 3 | 2025 | linked to commercial hub deveopment
PFW1 | Piopiotahi | Ferry Terminal | Deconstruction - Ferry Terminal | Removal of Structures/Buildings at existing ferry terminal | m2 | 1300 | 392000 | 10 | 2032 | 1 | 2033
PFW2 | Piopiotahi | Ferry Terminal | Ferry Terminal Toilet Block | Toilet block with 4-5 pans to replace the facilities currently available at the Ferry Terminal | no. | 1 | 758000 | 10 | 2032 | 1 | 2033 | Assumed part of staged development for the site - Linked to Deconstruction of Ferry Terminal
PFW3 | Piopiotahi | Tracks & observation points | Bowen Falls Pontoon Walkway | Pontoon walkway connecting Ferry Terminal to the lower Bowen Falls Walkway | m | 130 | 810000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CKF1 | Corridor | Knobs flat experience hub | Knobs Flat Accomodation - Cabins | Basic cabins established at Knobs Flat to complement the existing facilities. Allowing for 4 new structures within the development | m2 | 330 | 2496000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CKF2 | Corridor | Knobs flat experience hub | Knobs Flat Accomodation - Camping development | Development of the camp offering in the area surrounding the cabins including landscaping and upgraded services / facilities. Non-powered sites | m2 | 16000 | 3865000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CKF3 | Corridor | Knobs flat experience hub | Knobs Flat Interpretive Structures | Facilities located within Knobs Flat providing education / information | no. | 2 | 1401000 | 15 | 2037 | 2 | 2039 | As funding permits, developed with balance of site |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CKF4 | Corridor | Knobs flat experience hub | Knobs Flat Interpretive Building | Interpretive building providing temporary shelter, hall style with single level to potentially act as a community facility | m2 | 100 | 731000 | 15 | 2037 | 2 | 2039 | As funding permits, developed with balance of site |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CKF5 | Corridor | Knobs flat experience hub | Knobs Flat Walking Track - Abled Body | Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) | m | 2400 | 1949000 | 15 | 2037 | 2 | 2039 | As funding permits, developed with balance of site |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CKF6 | Corridor | Knobs flat experience hub | Knobs Flat Walking Track - Accessible | Wheelchair accessible Track (assumes establishment on existing cut, ease of access and flat @ Knobs Flat) | m | 1000 | 569000 | 15 | 2037 | 2 | 2039 | As funding permits, developed with balance of site |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CKF7 | Corridor | Knobs flat experience hub | Services - Potable Water | Additions to the existing potable water distribution network to support proposed development |  |  | 233000
CKF8 | Corridor | Knobs flat experience hub | Services - Wastewater | Additions to the existing wastewater collection network to support proposed development, including new toilet block and enhancement of treatment |  |  | 868000
CKF9 | Corridor | Knobs flat accommodation hub | Kiosk Creek Accomodation - Lodge | 25 bed (assumed 30% of footprint of accommodation at Piopiotahi) at Kiosk Creek. Will have limitations due to ability to service. | m2 | 462 | 5629000 | 15 | 2037 | 2 | 2039 | As funding permits, developed with balance of site
CKF10 | Corridor | Knobs flat accommodation hub | Kiosk Creek Accomodation - Wastewater | Wastwater treatment system based on small catchment and disposal to ground, noting that there are poor conditions and a vaulted system may be required. | no. | 1 | 2415000 | 15 | 2037 | 2 | 2039 | As funding permits, developed with balance of site
CKF11 | Corridor | Knobs flat experience hub | Knobs Flat Flood Protection | Stop banks and flood protection structures required for Knobs Flat Accomodation | m | 3000 | 21918000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CCE1 | Corridor | Homer Tunnel portals | Homer Tunnel - Eastern Portal | Expansion of eastern Tunnel Portal for viewing area providing rockfall protection from the southern slopes, and protected pullover area for buses allowing for the visitor experience. | no. | 1 | 52516000 | 0 | 2022 | 4 | 2026 | Base Option Design Yr 1, Construct Yr 2-4
CCE2 | Corridor | Homer Tunnel portals | Homer Tunnel - Western Portal Loop 2 | Parking Area enhancement at Loop 2 - including a robust shelter, 900 m2 parking, 75m retaining wall | no. | 1 | 1614000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CCE3 | Corridor | FNP threshold | Corridor Experience - FNP Entrance / Departure | Constructed entrance developed along lines of kiosk and remote monitoring | no. | 1 | 701000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CCE4 | Corridor | FNP threshold | Corridor Experience - Eglington Reveal Carpark | Parking Area at Eglington Reveal- including a robust shelter, 900 m2 parking (unsealed), and 4 vaulted toilets | no. | 1 | 1338000
CCE5 | Corridor | FNP threshold | Corridor Interpretation | Budget allowance for the establishment of interpretive materials throughout Corridor (Signage, Displays, Services) | no. | 1 | 1000000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CCE6 | Corridor | Short Stops | Cycleway - Knobs Flat to Cascade Creek | Established cycleway, typically off road, between the two locations | m | 12700 | 16109000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CCE7 | Corridor | Short Stops | Cycleway - Knobs Flat from Te Anau Downs | Established cycleway, typically off road, between the two locations | m | 29500 | 37418000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CCE8 | Corridor | Short Stops | Bus Shelter - Light | Simple shelter either waterproof stretch awning attached between poles in peak season or simple solid roof (site dependant), with a single sealed vault toilet. Internet /wifi / mobile connection allowed for (site dependant) | no. | 5 | 709000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CCE9 | Corridor | Short Stops | Bus Shelter - Minor | Timber lined structure and interpretation boards. Waterproof stretch side awning attached in peak season to increase capacity, with a single sealed vault toilet. Internet /wifi / mobile connection allowed for (site dependant) | no. | 5 | 2028000
CTH1 | Corridor | Super track head | Super Track Head - Experience Hub | Super Track Head - Facility associated with the exposing visitors to the history and significance of the area to Mana Whenua, provide an information centre for the local region | m2 | 200 | 2030000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH2 | Corridor | Super track head | Super Track Head - Parking Area | Super Track Head - Parking for Lake Marian walkway/ trail head. Enhancement of the existing parking area | m3 | 500 | 193000 | 1 | 2023 | 4 | 2027 | Base Option Design Yr 1, Construct Yr 2/4 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH3 | Corridor | Super track head | Super Track Head - Wastewater Services | Vaulted collection system, with 3-4 pans (toilet block) | no. | 1 | 716000
CTH4 | Corridor | Super track head | Super Track Head - Potable Water Services | Package water supply and treatment for servicing super track head, with intake from the Hollyford River | no. | 1 | 1320000
CTH5 | Corridor | Super track head | Super Track Head - Power | Developed low head power turbine for on site power generation, allows for intake, ducting, turbine and generator, and conection to Super Track Head Experience Hub | no. | 1 | 2233000
CTH6 | Corridor | Super track head | Walking Track - Lake Marian Loop | (From Track Head) Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) | m | 3100 | 2517000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH7 | Corridor | Super track head | Walking Track - Waterfall Loop | (From Track Head) Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) | m | 2850 | 2314000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH8 | Corridor | Super track head | Walking Track - Nature Loop | (From Track Head) Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) | m | 2300 | 1868000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH9 | Corridor | Super track head | Walking Track - Track Head to Key Summit | (From Track Head) Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) | m | 2700 | 2192000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH10 | Corridor | Super track head | Walking Track - Cascade Creek to Key Summit | (From Track Head) Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) | m | 12900 | 10472000 | 1 | 2023 | 4 | 2027 | Base Option Design Yr 1, Construct Yr 2/4 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH11 | Corridor | Super track head | Walking Track - Lake Howden - Upgrade | (From Track Head) Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) Upgrade at 50% of full development cost | m | 4500 | 1827000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH12 | Corridor | Super track head | Walking Track - Track Head to Hollyford Track | (From Track Head) Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) | m | 7000 | 5683000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
TAV1 | Te Anau | Visitor Hub | Structures - Visitor Experience Hub - Te Anau | Facility developed to act as the focal point for the overall experience in Te Anau. Ticketing, interactive displays, information, services. | m2 | 1000 | 10259000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
TAV2 | Te Anau | Visitor Hub | Landscaping - Visitor Experience Hub - Te Anau | Provison for an enhanced enviroment including paving and landscaping surrounding the Visitor Hub | m2 | 10000 | 5130000
TAV3 | Te Anau | Visitor Hub | Structures - Bus Stop - Te Anau Departure | Shelter / Refuge style of development acting as a departure point for buses. Located adjacent to the Visitor Experience Hub | no. | 1 | 684000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
TAV4 | Te Anau | Visitor Hub | Pavements - Visitor Experience Hub - Te Anau | Parking provided for drop off and short term carparking and for Bus Transfers. Allowance for the equivalent of 60 vehicle parks | no. | 60 | 990000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
TAV5 | Te Anau | Visitor Hub | Services - Wastewater | Modification required to the wastewater systems in the vicinity of the Visitor Hub including connection costs to the Council Network |  |  | 152000
TAV6 | Te Anau | Visitor Hub | Services - Potable Water | Modification required to the potable water systems in the vicinity of the Visitor Hub including connection costs to the Council Network |  |  | 123000
TAV7 | Te Anau | Visitor Hub | Structure - Jetty | Jetty facility that would align with the Visitor Hub. Developed based on demand at location | m | 50 | 992000
TAV8 | Te Anau | Visitor Hub | Carriageway - Visitor Experience Hub - Te Anau | Allowance for the realignment of roadways in the vicinity of the visitor hub and intersection upgrades for the movement of buses etc within Te Anau. Scope would require definition based on final selected location | m | 1000 | 3430000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
TAV9 | Te Anau | Visitor Hub | Te Anau Interpretation | Budget allowance for the establishment of interpretive materials throughout Te Anau (Signage, Displays, Services, incl. within the hub) | no. | 1 | 1000000
TAB1 | Te Anau | Transport Terminal | Buses - Base of Operations | Area for the operation and maintenance of buses to take visitors from Te Anau to Piopiotahi. Includes facilities for Bus driver resting, bus mainteance, charging and overnight housing |  |  | 16804000
TAB2 | Te Anau | Transport Terminal | Pavements - Park and Ride - Te Anau | Car Parking (Spaces) for Park and Ride. To be established adjacent to the Base of Operations for buses to make use of shared facilities, and to optimise the use of the pavement areas (peak season the bus storage area can be used for overflow parking) | no. | 1000 | 16849000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
TAB3 | Te Anau | Access Systems | Buses - Capital Investment | Selected bus infrastructure for the conveyance of visitors to and from Piopiotahi | no. | 156 | 141804000
RELEASED BY THE MINISTER OF CONSERVATION
RELEASED BY THE MINISTER OF CONSERVATION

## Cost_Estimates
[10 empty] | 20% | 15% |  |  | 6% | 2% | 6% |  | 20% |  | Baseline Year | 2022
ID | Location | Category | CBA_Reference | Description | Comment | Unit | Unit_Price | Quantity_Max | Base_Cost | Scope_of_Works_Uncertainty | Contractor_(P&G) | Location_ExtraOver_(%) | Location_ExtraOver_($) | Fees_Design | Fees_Consent_ Tender | Fees_Construction | Fee_Estimate | Contingency | Cost_Estimate | Year_Established | Year_Established | Construction_Duration | Completion | Development_Comments | Life_Expectancy | OPEX_(Annual) | OPEX_Comments
PHub3 | Piopiotahi | Structures | Visitor Accomodation | Accomodation - Visitors | 100 bed accommodation targetting overnight stays, styled as a 3 Star Hotel, resilient to withstand extreme events and act as a refuge. | m2 | 6380 | 1540 | [10 empty] | 21120000
| Piopiotahi | Structures | Visitor Accomodation | Baseline - Accomodation 3 star | 100 bed | m2 | 5800 | 1540 | 8932000 | 1786400 | 1607760 | 10% | 1232616 | 10% | 2% | 6% | 2440579.68 | 3199871.136 | 19200000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Piopiotahi | Structures | Visitor Accomodation | Extra Over - Accomodation 3 Star - PioPiotahi | Resilience improvements/refuge at Accomodation - needs site-specific assessment and design | m2 | 580 | 1540 | 893200 | 178640 | 160776 | 10% | 123261.6 | 10% | 2% | 6% | 244057.968 | 319987.1136 | 1920000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
PHub4 | Piopiotahi | Structures | Staff Accomodation | Accomodation - Staff | 280-320 bed accommodation for staff, some single units and some shared rooms, resilient to withstand extreme events and act as a refuge. | m2 | 3960 | 5100 | [10 empty] | 43412000
| Piopiotahi | Structures | Staff Accomodation | Baseline - Accomodation-Staff |  | m2 | 3600 | 5100 | 18360000 | 3672000 | 3304800 | 10% | 2533680 | 10% | 2% | 6% | 5016686.4 | 6577433.28 | 39465000 | 15 | 2037 | 2 | 2039 | As funding permits, use existing accomodation until required
| Piopiotahi | Structures | Staff Accomodation | Extra Over - Accomodation-Staff | Resilience improvements/refuge at Staff Accomodation - needs site-specific assessment and design | m2 | 360 | 5100 | 1836000 | 367200 | 330480 | 10% | 253368 | 10% | 2% | 6% | 501668.64 | 657743.328 | 3947000 | 15 | 2037 | 2 | 2039 | As funding permits, use existing accomodation until required
PDel2 | Piopiotahi | Structures | Tracks & observation points | Visitor Protection Refuges | Shelter / Refuge for hazards at key locations outside of the key structures (at Fresh Water Basin, Long Stay Parking, Deepwater Basin, Cleddau Delta). Double as infromation centres and potential observation points | no. | 345000 | 4 | 1380000 | 276000 | 248400 | 10% | 190440 | 10% | 2% | 6% | 377071.2 | 494382.24 | 2967000 | 0 | 2022 | 2 | 2024 | Base Option Design Yr 1, Construct Yr 2
PHub7 | Piopiotahi | Structures | Arrival | Structures - Bus Stop - Piopiotahi arrival | Shelter / Refuge style of development acting as an arrival point for buses. Located a short distance from the Visitor Experience Hub | no. | 345000 | 1 | 345000 | 69000 | 62100 | 10% | 47610 | 6% | 2% | 6% | 73319.4 | 119405.88 | 717000 | 0 | 2022 | 2 | 2024 | Base Option Design Yr 1, Construct Yr 2
PHub8 | Piopiotahi | Structures | Arrival | Structures - Covered Walkway - Piopiotahi arrival | Covered Walkway from Bus Arrival to Visitor Experience Hub | m | 1840 | 170 | 312800 | 62560 | 56304 | 10% | 43166.4 | 6% | 2% | 6% | 66476.256 | 108261.3312 | 650000 | 0 | 2022 | 2 | 2024 | Base Option Design Yr 1, Construct Yr 2
PHub5 | Piopiotahi | Structures | Marine Centre | Marine Interpretive Centre - Piopiotahi | Facility developed to enhance visitor interaction. Touch pool, working lab, concourse/display area, back of house. Proposed adjacent to or part of Visitor Experience Hub. | m2 | 5500 | 950 | 5225000 | [9 empty] | 11233000
| Piopiotahi | Structures | Marine Centre | Baseline - Marine Interpretive Centre - PioPiotahi |  | m2 | 5000 | 950 | 4750000 | 950000 | 855000 | 10% | 655500 | 10% | 2% | 6% | 1297890 | 1701678 | 10211000 | 15 | 2037 | 2 | 2039 | As funding permits, developed with balance of site
| Piopiotahi | Structures | Marine Centre | Extra Over - Marine Interpretive Centre - PioPiotahi | Resilience improvements/refuge at Marine Interpretive Centre - needs site-specific assessment and design | m2 | 500 | 950 | 475000 | 95000 | 85500 | 10% | 65550 | 10% | 2% | 6% | 129789 | 170167.8 | 1022000 | 15 | 2037 | 2 | 2039 | As funding permits, developed with balance of site
PHub2 | Piopiotahi | Structures | Visitor Hub | Visitor Experience Hub - Piopiotahi | Facility developed to act as the focal point for the overall experience. Ticketing, interactive displays, information, services. Proposed adjacent to or including Marine Interpretive Centre. | m2 |  | 1800 | [10 empty] | 21281000 | 0 | 2022 | 3 | 2025
| Piopiotahi | Structures | Visitor Hub | Baseline_Visitor Experience Hub - PioPiotahi |  | m2 | 5000 | 1800 | 9000000 | 1800000 | 1620000 | 10% | 1242000 | 10% | 2% | 6% | 2459160 | 3224232 | 19346000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Piopiotahi | Structures | Visitor Hub | Extra Over - Visitor Experience Hub - PioPiotahi | Resilience improvements/refuge at Piopiotahi - needs site-specific assessment and design | m2 | 500 | 1800 | 900000 | 180000 | 162000 | 10% | 124200 | 10% | 2% | 6% | 245916 | 322423.2 | 1935000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
PDW2 | Piopiotahi | Facilities | Commercial Fishing Port | Deepwater Basin Experience Hub | Focus for tourist activities within Deepwater basin. To include a pavilion, boardwalk, food stalls, pavement and landscaping | [13 empty] | 2854000 | 0 | 2022 | 3 | 2025 | Assumed Base Option Design Yr 1, Construct Yr 2/3
| Piopiotahi | Facilities | Commercial Fishing Port | Structures - Deepwater Basin Pavilion | Lightweight pavilion to act as focal point for experience in Deep Water Basin | m2 | 3600 | 100 | 360000 | 72000 | 64800 | 10% | 49680 | 10% | 2% | 6% | 98366.4 | 128969.28 | 774000 | 0 | 2022 | 3 | 2025 | Assumed Base Option Design Yr 1, Construct Yr 2/3
| Piopiotahi | Facilities | Commercial Fishing Port | Pavements - Deepwater Basin Walkway | Raised walkway area / boardwalk to direct tourist within the area | m | 400 | 120 | 48000 | 9600 | 8640 | 10% | 6624 | 6% | 2% | 6% | 10200.96 | 16612.992 | 100000
| Piopiotahi | Facilities | Commercial Fishing Port | Pavements - Deepwater Basin Food Stalls | Sealed area adjacent to the Pavilion (approx 50 x 20m) to allow for food stalls and services for visitors | m2 | 250 | 1000 | 250000 | 50000 | 45000 | 10% | 34500 | 6% | 2% | 6% | 53130 | 86526 | 520000
| Piopiotahi | Facilities | Commercial Fishing Port | Landscaping - Deepwater Basin Experience | Area wide treatment of the existing surface to accommodate visitor movements | m2 | 190 | 3700 | 703000 | 140600 | 126540 | 10% | 97014 | 6% | 2% | 6% | 149401.56 | 243311.112 | 1460000
PDW1 | Piopiotahi | Structures | Commercial Fishing Port | Structures - Operations - Commercial port | Renewal of the existing building that houses the operations for the Commerical Port | m2 |  | 300 | 0 | 0 | 0 | 10% | 0 | 10% | 2% | 6% | 0 | 0 | 2413000 | 0 | 2022 | 3 | 2025 | Assumed Base Option Design Yr 1, Construct Yr 2/3
| Piopiotahi | Structures | Commercial Fishing Port | Structures - Operations - Commercial port | Building / structure for commerical operations at the port | m2 | 3600 | 300 | 1080000 | 216000 | 194400 | 10% | 149040 | 10% | 2% | 6% | 295099.2 | 386907.84 | 2322000 | 0 | 2022 | 3 | 2025 | Assumed Base Option Design Yr 1, Construct Yr 2/3
| Piopiotahi | Structures | Commercial Fishing Port | Deconstruct - Commercial Port Operations | Removal of Structures/Buildings at Commercial Port (current operations) | m2 | 140 | 300 | 42000 | 8400 | 7560 | 10% | 5796 | 10% | 2% | 6% | 11476.08 | 15046.416 | 91000 | 0 | 2022 | 3 | 2025 | Assumed Base Option Design Yr 1, Construct Yr 2/3
PHub1 | Piopiotahi | Structures | Visitor Hub | Deconstruction - Existing Hub | Removal of structures in the central hub to make way for Visitor Experience, Accommodation and Marine Centre | m2 | 140 | 6125 | 857500 | 171500 | 154350 | 10% | 118335 | 10% | 2% | 6% | 234303.3 | 307197.66 | 1844000 | 0 | 2022 | 1 | 2023
PFW1 | Piopiotahi | Structures | Ferry Terminal | Deconstruction - Ferry Terminal | Removal of Structures/Buildings at existing ferry terminal | m2 | 140 | 1300 | 182000 | 36400 | 32760 | 10% | 25116 | 10% | 2% | 6% | 49729.68 | 65201.136 | 392000 | 10 | 2032 | 1 | 2033
PHub6 | Piopiotahi | Structures | Staff Accomodation | Deconstruction - Staff Accommodation | Removal of Existing Housing and Staff accommodation in preparation for new infrastructure | m2 | 140 | 2850 | 399000 | 79800 | 71820 | 10% | 55062 | 10% | 2% | 6% | 109022.76 | 142940.952 | 858000 | 17 | 2039 | 1 | 2040 | As funding permits, requires new staff accommodation to be built
PFW2 | Piopiotahi | Structures | Ferry Terminal | Ferry Terminal Toilet Block | Toilet block with 4-5 pans to replace the facilities currently available at the Ferry Terminal | no. | 352500 | 1 | 352500 | 70500 | 63450 | 10% | 48645 | 10% | 2% | 6% | 96317.1 | 126282.42 | 758000 | 10 | 2032 | 1 | 2033 | Assumed part of staged development for the site - Linked to Deconstruction of Ferry Terminal
PExO2 | Piopiotahi | Transport | Aerodrome | Pavements - Taxiway Realignment | For Planes - Revised position of taxiway as an extra over sum for the total runway reconstruction (on south side of the runway) | m2 | 125 | 16000 | 2000000 | 400000 | 360000 | 10% | 276000 | 6% | 2% | 6% | 425040 | 692208 | 4154000 | 0 | 2022 | 2 | 2024 | Require Option where visitor hub on terrace. Will require staff accomodation to be moved accelerating this to year 0. Will impact timing of all other elements in this table.
PDel3 | Piopiotahi | Transport | Parking | Pavements - New Parking Area Sealed | Long stay parking and bus layover area. To be established within the footprint of the existing staff accommodation area. | m2 | 250 | 6000 | 1500000 | 300000 | 270000 | 10% | 207000 | 6% | 2% | 6% | 318780 | 519156 | 3115000 | 0 | 2022 | 3 | 2025
PHub9 | Piopiotahi | Transport | Road Realignment | Pavements - Realignment (Arrival) | New access into Piopiotahi established to bring the road (as a one way system) onto the alignment of the existing taxiway | m2 | 1297.5 | 500 | 648750 | 129750 | 116775 | 10% | 89527.5 | 6% | 2% | 6% | 137872.35 | 224534.97 | 1348000 | 0 | 2022 | 3 | 2025 | Changed alignment for moving from two-way to one way for arrival access
PExO1 | Piopiotahi | Transport | Aerodrome | Pavements - Runway reconstruction | Remove existing pavement and rebuild the runway, 800m x 20m plus taxiway and terminal area. Elevate 50% of runway, out of the coastal flooding area | m2 | 385.5 | 32000 | 12336000 | 2467200 | 2220480 | 10% | 1702368 | 6% | 2% | 6% | 2621646.72 | 4269538.944 | 25618000 | 5 | 2027 | 2 | 2029 | Assumed existing pavement will have between 0-10 years before full replacement required. Appliciable only where aerodrome retained.
PDel1 | Piopiotahi | Transport | Tracks & observation points | Deconstruction - Airport Runway | Removal of existing runway and pavement areas. Establish either landscaping features / planting or establish locations for helicopter landings in its place. | m2 | 131 | 16000 | 2096000 | 419200 | 377280 | 10% | 289248 | 10% | 2% | 6% | 572711.04 | 750887.808 | 4506000 | 2 | 2024 | 1 | 2025 | Delayed start tied into visitor hub development
PHub11 | Piopiotahi | Transport | Visitor Hub | Deconstruction - Foreshore Carparking | Removal of existing carparking and pavement on the foreshore. Establish landscaping features / plantings in its place. | m2 | 131 | 5700 | 746700 | 149340 | 134406 | 10% | 103044.6 | 10% | 2% | 6% | 204028.308 | 267503.7816 | 1606000 | 2 | 2024 | 1 | 2025 | Delayed start tied into visitor hub development
PHub10 | Piopiotahi | Facilities | Visitor Hub | Landscaping - Visitor Experience Hub - Piopiotahi | Water front development - to provide an enhanced enviroment including boardwalks, paving and landscaping surrounding the Visitor Hub | m2 | 250 | 10000 | 2500000 | 500000 | 450000 | 10% | 345000 | 6% | 2% | 6% | 531300 | 865260 | 5192000
PDel5 | Piopiotahi | Transport | Access Systems | Shuttles - Capital Investment | Purchase of shuttles to convey visitors from from Visitor Experience Hub to the ferry terminal. | no. | 750000 | 12 | [10 empty] | 10908000
| Piopiotahi | Transport | Access Systems | Shuttles | Vehicles for movement of visitors from hub to ferry terminal. Low rider, high volume about 8 on constant loop - 75% year 0 | no. | 750000 | 9 | 6750000 | 0 | 0 | 0% | 0 | 0% | 1% | 0% | 67500 | 1363500 | 8181000 | 3 | 2025 | 0 | 2025 | Initial portion of fleet - needs Shuttle base completed before purchase
| Piopiotahi | Transport | Access Systems | Shuttles | Vehicles for movement from hub to ferry terminal. Low rider, high volume about 8 on constant loop - 25% year 15 | no. | 750000 | 3 | 2250000 | 0 | 0 | 0% | 0 | 0% | 1% | 0% | 22500 | 454500 | 2727000 | 15 | 2037 | 1 | 2038 | second portion of fleet
PDel4 | Piopiotahi | Transport | Transport Terminal | Shuttles - Base of Operations | Area for the operation and maintenance of shuttles to take visitors from the hub to the terminal. Includes facilities for Bus driver resting, shuttle mainteance, charging and overnight housing | [13 empty] | 4571000
| Piopiotahi | Transport | Transport Terminal | Shuttles - Base | Established adjacent to Long stay parking and bus layover area. To be established within the footprint of the existing staff accommodation area. Housing of shuttles - includes allowance for charging hubs | m2 | 190 | 2460 | 467400 | 93480 | 84132 | 10% | 64501.2 | 6% | 2% | 6% | 99331.848 | 161769.0096 | 971000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Piopiotahi | Transport | Transport Terminal | Shuttles - Base | Building / structure for drivers and maintenance | m2 | 3600 | 400 | 1440000 | 288000 | 259200 | 10% | 198720 | 10% | 2% | 6% | 393465.6 | 515877.12 | 3096000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Piopiotahi | Transport | Transport Terminal | Shuttles - Base (Generator) | Power for charging hubs - Backup generator | no. | 116840 | 1 | 116840 | 23368 | 21031.2 | 10% | 16123.92 | 6% | 2% | 6% | 24830.8368 | 40438.7914 | 243000 | 2 | 2024 | 1 | 2025
| Piopiotahi | Transport | Transport Terminal | Shuttles - Base (Transformer) | Power for charging hubs - Transformer | no. | 125250 | 1 | 125250 | 25050 | 22545 | 10% | 17284.5 | 6% | 2% | 6% | 26618.13 | 43349.526 | 261000 | 2 | 2024 | 1 | 2025
PHub12 | Piopiotahi | 3 Waters | Wastewater | Services - Wastewater | Allowance for alteration of the existing wastewater network to accommodate the proposed developments within Piopiotahi. Upgrade to the current plant provided for with a higher rate and quality treatment to meet potential revised consent requirements | [13 empty] | 2250000
| Piopiotahi | 3 Waters | Wastewater | WW - Pipelines | Allowance to realign existing WW near the Hub | m | 185 | 1200 | 222000 | 44400 | 39960 | 10% | 30636 | 6% | 2% | 6% | 47179.44 | 76835.088 | 462000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Piopiotahi | 3 Waters | Wastewater | WW - Manholes |  | no. | 4700 | 15 | 70500 | 14100 | 12690 | 10% | 9729 | 6% | 2% | 6% | 14982.66 | 24400.332 | 147000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Piopiotahi | 3 Waters | Wastewater | WW - Treatment (upgrade to existing with Consent renewal in 2028) | Allowance to modify the existing treatment facility for high rate treatment and continued outfall | no. | 790000 | 1 | 790000 | 158000 | 142200 | 10% | 109020 | 6% | 2% | 6% | 167890.8 | 273422.16 | 1641000 |  | 2026 | 2 | 2028 | Upgrades required to WWTP likely to comply with possible changes in consent conditions. Dates locked.
PHub13 | Piopiotahi | 3 Waters | Potable Water | Services - Potable Water | Allowance for alteration of the existing potable water network to accommodate the proposed developments within Piopiotahi. Increased storage (500m3) provided for. | [13 empty] | 1603000
| Piopiotahi | 3 Waters | Potable Water | PW - Pipelines | Allowance to realign existing PW near Hub | m | 165 | 1800 | 297000 | 59400 | 53460 | 10% | 40986 | 6% | 2% | 6% | 63118.44 | 102792.888 | 617000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Piopiotahi | 3 Waters | Potable Water | PW - Valves |  | no. | 1750 | 14 | 24500 | 4900 | 4410 | 10% | 3381 | 6% | 2% | 6% | 5206.74 | 8479.548 | 51000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Piopiotahi | 3 Waters | Potable Water | PW - Storage | Storage to increase the half day storage currently available | no. | 450000 | 1 | 450000 | 90000 | 81000 | 10% | 62100 | 6% | 2% | 6% | 95634 | 155746.8 | 935000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
PHub14 | Piopiotahi | Facilities | Power | Services - Power Supply | Allowance for replacement of the existing turbines and generators (and equipment) to accommodate the proposed developments within Piopiotahi. | [13 empty] | 4993000
| Piopiotahi | Facilities | Power | Power Generation | Supply and installation of 500kW Turbine and Generator | no. | 1100000 | 2 | 2200000 | 440000 | 396000 | 10% | 303600 | 6% | 2% | 6% | 467544 | 761428.8 | 4569000
| Piopiotahi | Facilities | Power | Power Cabling | Allowance to realign existing power near the Hub | m | 170 | 1200 | 204000 | 40800 | 36720 | 10% | 28152 | 6% | 2% | 6% | 43354.08 | 70605.216 | 424000
PHub16 | Piopiotahi | Facilities | Tracks & observation points | Piopiotahi Viewing Deck Walkway | Redevelopment of the existing walkway above the hub to including treetop canopy viewing platforms and a link to the Visitor Experience Hub | [13 empty] | 1341000
| Piopiotahi | Facilities | Tracks & observation points | Viewing Deck - Timber and Steel Platform | Timber and Steel viewing platforms, assumed that there will be two locations in the canopy of the trees at approx. 100-150m2 each | m2 | 1250 | 300 | 375000 | 75000 | 67500 | 10% | 51750 | 6% | 2% | 6% | 79695 | 129789 | 779000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Piopiotahi | Facilities | Tracks & observation points | Walkway / Bridge - Visitor Experience Hub | Steel framed walkway/bridge to connect from the Visitor Experience Hub to the start of the Viewing Deck walkway. Budget based on the GFA rate for the Visitor Experience Hub | m | 5000 | 30 | 150000 | 30000 | 27000 | 10% | 20700 | 6% | 2% | 6% | 31878 | 51915.6 | 312000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Piopiotahi | Facilities | Tracks & observation points | Walking Track - Abled Body | Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) | m | 400 | 300 | 120000 | 24000 | 21600 | 10% | 16560 | 6% | 2% | 6% | 25502.4 | 41532.48 | 250000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
PDel6 | Piopiotahi | Facilities | Tracks & observation points | Delta Walking Track - Accessible | Accessible walking track developed through the Delta being mindful to minimise the physical footprint of the works. | m | 400 | 3600 | 1440000 | 288000 | 259200 | 10% | 198720 | 6% | 2% | 6% | 306028.8 | 498389.76 | 2991000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
PHub15 | Piopiotahi | Facilities | Visitor Hub | Piopiotahi Interpretation | Budget allowance for the establishment of interpretive materials throughout Piopiotahi (Signage, Displays, Services, incl. within the hub) | no. |  | 1 | [10 empty] | 2000000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
PHub17 | Piopiotahi | Facilities | Tracks & observation points | Walking Track - Accessible (Premium) | Wheelchair accessible Track (corridor access around the Visitor Hub not otherwise covered under the water front development). | m | 470 | 1000 | 470000 | 94000 | 84600 | 10% | 64860 | 6% | 2% | 6% | 99884.4 | 162668.88 | 977000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
PDel7 | Piopiotahi | Facilities | Tracks & observation points | Walking Track - Milford Lodge to Tutoko Bridge | Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards). Along SH94 alignment for 2000m and then 4000m upgrade alongside the Tutoko River | m | 400 | 4000 | 1600000 | 320000 | 288000 | 10% | 220800 | 6% | 2% | 6% | 340032 | 553766.4 | 3323000 | 0 | 2022 | 3 | 2025
PFW3 | Piopiotahi | Facilities | Tracks & observation points | Bowen Falls Pontoon Walkway | Pontoon walkway connecting Ferry Terminal to the lower Bowen Falls Walkway | m | 3000 | 130 | 390000 | 78000 | 70200 | 10% | 53820 | 6% | 2% | 6% | 82882.8 | 134980.56 | 810000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
PDW3 | Piopiotahi | Facilities | Commercial Fishing Port | Kayak Landing point | Developed on the basis of a floating pontoon. This could be developed as a modified concrete boat ramp instead | m | 3000 | 50 | 150000 | 30000 | 27000 | 10% | 20700 | 6% | 2% | 6% | 31878 | 51915.6 | 312000 | 0 | 2022 | 3 | 2025 | linked to commercial hub deveopment
CKF1 | Corridor | Structures | Knobs flat experience hub | Knobs Flat Accomodation - Cabins | Basic cabins established at Knobs Flat to complement the existing facilities. Allowing for 4 new structures within the development | m2 | 3600 | 330 | 1188000 | 237600 | 213840 | 7.5% | 122958 | 10% | 2% | 6% | 317231.64 | 415925.928 | 2496000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CKF2 | Corridor | Structures | Knobs flat experience hub | Knobs Flat Accomodation - Camping development | Development of the camp offering in the area surrounding the cabins including landscaping and upgraded services / facilities. Non-powered sites | m2 | 119 | 16000 | 1904000 | 380800 | 342720 | 7.5% | 197064 | 6% | 2% | 6% | 395441.76 | 644005.152 | 3865000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CKF7 | Corridor | 3 Waters | Knobs flat experience hub | Services - Potable Water | Additions to the existing potable water distribution network to support proposed development | [13 empty] | 233000
| Corridor | 3 Waters | Knobs flat experience hub | PW - Pipelines (Knobs Flat) | "Knobs Flat" Assumed conveyance to Kiosk Creek | m | 165 | 640 | 105600 | 21120 | 19008 | 7.5% | 10929.6 | 6% | 2% | 6% | 21932.064 | 35717.9328 | 215000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Corridor | 3 Waters | Knobs flat experience hub | PW - Valves (Knobs Flat) |  | no. | 1750 | 5 | 8750 | 1750 | 1575 | 7.5% | 905.625 | 6% | 2% | 6% | 1817.2875 | 2959.5825 | 18000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CKF8 | Corridor | 3 Waters | Knobs flat experience hub | Services - Wastewater | Additions to the existing wastewater collection network to support proposed development, including new toilet block and enhancement of treatment | [13 empty] | 868000
| Corridor | 3 Waters | Knobs flat experience hub | WW - Pipelines (Knobs Flat) | "Knobs Flat" Assumed conveyance to Kiosk Creek | m | 185 | 300 | 55500 | 11100 | 9990 | 7.5% | 5744.25 | 6% | 2% | 6% | 11526.795 | 18772.209 | 113000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Corridor | 3 Waters | Knobs flat experience hub | WW - Manholes (Knobs Flat) |  | no. | 4700 | 4 | 18800 | 3760 | 3384 | 7.5% | 1945.8 | 6% | 2% | 6% | 3904.572 | 6358.8744 | 39000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Corridor | 3 Waters | Knobs flat experience hub | WW - Treatment / Toilets (Knobs Flat) | "Knobs Flat" Assumed facilities at Kiosk Creek | no. | 352500 | 1 | 352500 | 70500 | 63450 | 7.5% | 36483.75 | 6% | 2% | 6% | 73210.725 | 119228.895 | 716000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CKF6 | Corridor | Facilities | Knobs flat experience hub | Knobs Flat Walking Track - Accessible | Wheelchair accessible Track (assumes establishment on existing cut, ease of access and flat @ Knobs Flat) | m | 280 | 1000 | 280000 | 56000 | 50400 | 0.075 | 28980 | 0.06 | 0.02 | 0.06 | 58153.2 | 94706.64 | 569000 | 15 | 2037 | 2 | 2039 | As funding permits, developed with balance of site |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CKF5 | Corridor | Facilities | Knobs flat experience hub | Knobs Flat Walking Track - Abled Body | Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) | m | 400 | 2400 | 960000 | 192000 | 172800 | 7.5% | 99360 | 6% | 2% | 6% | 199382.4 | 324708.48 | 1949000 | 15 | 2037 | 2 | 2039 | As funding permits, developed with balance of site |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CKF3 | Corridor | Facilities | Knobs flat experience hub | Knobs Flat Interpretive Structures | Facilities located within Knobs Flat providing education / information | no. | 345000 | 2 | 690000 | 138000 | 124200 | 7.5% | 71415 | 6% | 2% | 6% | 143306.1 | 233384.22 | 1401000 | 15 | 2037 | 2 | 2039 | As funding permits, developed with balance of site |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CKF4 | Corridor | Facilities | Knobs flat experience hub | Knobs Flat Interpretive Building | Interpretive building providing temporary shelter, hall style with single level to potentially act as a community facility | m2 | 3600 | 100 | 360000 | 72000 | 64800 | 7.5% | 37260 | 6% | 2% | 6% | 74768.4 | 121765.68 | 731000 | 15 | 2037 | 2 | 2039 | As funding permits, developed with balance of site |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CKF10 | Corridor | 3 Waters | Knobs flat accommodation hub | Kiosk Creek Accomodation - Wastewater | Wastwater treatment system based on small catchment and disposal to ground, noting that there are poor conditions and a vaulted system may be required. | no. | 1189500 | 1 | 1189500 | 237900 | 214110 | 7.5% | 123113.25 | 6% | 2% | 6% | 247047.255 | 402334.101 | 2415000 | 15 | 2037 | 2 | 2039 | As funding permits, developed with balance of site
CKF9 | Corridor | Structures | Knobs flat accommodation hub | Kiosk Creek Accomodation - Lodge | 25 bed (assumed 30% of footprint of accommodation at Piopiotahi) at Kiosk Creek. Will have limitations due to ability to service. | m2 | 5800 | 462 | 2679600 | 535920 | 482328 | 7.5% | 277338.6 | 10% | 2% | 6% | 715533.588 | 938144.0376 | 5629000 | 15 | 2037 | 2 | 2039 | As funding permits, developed with balance of site
CKF11 | Corridor | Structures | Knobs flat experience hub | Knobs Flat Flood Protection | Stop banks and flood protection structures required for Knobs Flat Accomodation | m | 3600 | 3000 | 10800000 | 2160000 | 1944000 | 7.5% | 1117800 | 6% | 2% | 6% | 2243052 | 3652970.4 | 21918000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CCE8 | Corridor | Structures | Short Stops | Bus Shelter - Light | Simple shelter either waterproof stretch awning attached between poles in peak season or simple solid roof (site dependant), with a single sealed vault toilet. Internet /wifi / mobile connection allowed for (site dependant) | no. | 69800 | 5 | 349000 | 69800 | 62820 | 7.5% | 36121.5 | 6% | 2% | 6% | 72483.81 | 118045.062 | 709000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CCE9 | Corridor | Structures | Short Stops | Bus Shelter - Minor | Timber lined structure and interpretation boards. Waterproof stretch side awning attached in peak season to increase capacity, with a single sealed vault toilet. Internet /wifi / mobile connection allowed for (site dependant) | no. | 199800 | 5 | 999000 | 199800 | 179820 | 7.5% | 103396.5 | 6% | 2% | 6% | 207482.31 | 337899.762 | 2028000
CCE3 | Corridor | Transport | FNP threshold | Corridor Experience - FNP Entrance / Departure | Constructed entrance developed along lines of kiosk and remote monitoring | no. | 345000 | 1 | 345000 | 69000 | 62100 | 7.5% | 35707.5 | 6% | 2% | 6% | 71653.05 | 116692.11 | 701000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CCE4 | Corridor | Transport | FNP threshold | Corridor Experience - Eglington Reveal Carpark | Parking Area at Eglington Reveal- including a robust shelter, 900 m2 parking (unsealed), and 4 vaulted toilets | no. | 659200 | 1 | 659200 | 131840 | 118656 | 7.5% | 68227.2 | 6% | 2% | 6% | 136909.248 | 222966.4896 | 1338000
CCE1 | Corridor | Structures | Homer Tunnel portals | Homer Tunnel - Eastern Portal | Expansion of eastern Tunnel Portal for viewing area providing rockfall protection from the southern slopes, and protected pullover area for buses allowing for the visitor experience. | no. | 25000000 | 1 | 25000000 | 5000000 | 4500000 | 7.5% | 2587500 | 10% | 2% | 6% | 6675750 | 8752650 | 52516000 | 0 | 2022 | 4 | 2026 | Base Option Design Yr 1, Construct Yr 2-4
CCE2 | Corridor | Facilities | Homer Tunnel portals | Homer Tunnel - Western Portal Loop 2 | Parking Area enhancement at Loop 2 - including a robust shelter, 900 m2 parking, 75m retaining wall | no. | 795000 | 1 | 795000 | 159000 | 143100 | 7.5% | 82282.5 | 6% | 2% | 6% | 165113.55 | 268899.21 | 1614000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CCE5 | Corridor | Facilities | FNP threshold | Corridor Interpretation | Budget allowance for the establishment of interpretive materials throughout Corridor (Signage, Displays, Services) | no. |  | 1 | [10 empty] | 1000000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CCE6 | Corridor | Facilities | Short Stops | Cycleway - Knobs Flat to Cascade Creek | Established cycleway, typically off road, between the two locations | m | 625 | 12700 | 7937500 | 1587500 | 1428750 | 7.5% | 821531.25 | 6% | 2% | 6% | 1648539.375 | 2684764.125 | 16109000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CCE7 | Corridor | Facilities | Short Stops | Cycleway - Knobs Flat from Te Anau Downs | Established cycleway, typically off road, between the two locations | m | 625 | 29500 | 18437500 | 3687500 | 3318750 | 7.5% | 1908281.25 | 6% | 2% | 6% | 3829284.375 | 6236263.125 | 37418000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
CTH1 | Corridor | Facilities | Super track head | Super Track Head - Experience Hub | Super Track Head - Facility associated with the exposing visitors to the history and significance of the area to Mana Whenua, provide an information centre for the local region | m2 | 5000 | 200 | 1000000 | 200000 | 180000 | 7.5% | 103500 | 6% | 2% | 6% | 207690 | 338238 | 2030000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH2 | Corridor | Transport | Super track head | Super Track Head - Parking Area | Super Track Head - Parking for Lake Marian walkway/ trail head. Enhancement of the existing parking area | m3 | 190 | 500 | 95000 | 19000 | 17100 | 7.5% | 9832.5 | 6% | 2% | 6% | 19730.55 | 32132.61 | 193000 | 1 | 2023 | 4 | 2027 | Base Option Design Yr 1, Construct Yr 2/4 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH3 | Corridor | 3 Waters | Super track head | Super Track Head - Wastewater Services | Vaulted collection system, with 3-4 pans (toilet block) | no. | 352500 | 1 | 352500 | 70500 | 63450 | 7.5% | 36483.75 | 6% | 2% | 6% | 73210.725 | 119228.895 | 716000
CTH4 | Corridor | 3 Waters | Super track head | Super Track Head - Potable Water Services | Package water supply and treatment for servicing super track head, with intake from the Hollyford River | no. | 650000 | 1 | 650000 | 130000 | 117000 | 7.5% | 67275 | 6% | 2% | 6% | 134998.5 | 219854.7 | 1320000
CTH5 | Corridor | Power | Super track head | Super Track Head - Power | Developed low head power turbine for on site power generation, allows for intake, ducting, turbine and generator, and conection to Super Track Head Experience Hub | no. | 1100000 | 1 | 1100000 | 220000 | 198000 | 7.5% | 113850 | 6% | 2% | 6% | 228459 | 372061.8 | 2233000
CTH6 | Corridor | Facilities | Super track head | Walking Track - Lake Marian Loop | (From Track Head) Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) | m | 400 | 3100 | 1240000 | 248000 | 223200 | 7.5% | 128340 | 6% | 2% | 6% | 257535.6 | 419415.12 | 2517000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH7 | Corridor | Facilities | Super track head | Walking Track - Waterfall Loop | (From Track Head) Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) | m | 400 | 2850 | 1140000 | 228000 | 205200 | 7.5% | 117990 | 6% | 2% | 6% | 236766.6 | 385591.32 | 2314000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH8 | Corridor | Facilities | Super track head | Walking Track - Nature Loop | (From Track Head) Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) | m | 400 | 2300 | 920000 | 184000 | 165600 | 7.5% | 95220 | 6% | 2% | 6% | 191074.8 | 311178.96 | 1868000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH9 | Corridor | Facilities | Super track head | Walking Track - Track Head to Key Summit | (From Track Head) Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) | m | 400 | 2700 | 1080000 | 216000 | 194400 | 7.5% | 111780 | 6% | 2% | 6% | 224305.2 | 365297.04 | 2192000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH10 | Corridor | Facilities | Super track head | Walking Track - Cascade Creek to Key Summit | (From Track Head) Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) | m | 400 | 12900 | 5160000 | 1032000 | 928800 | 7.5% | 534060 | 6% | 2% | 6% | 1071680.4 | 1745308.08 | 10472000 | 1 | 2023 | 4 | 2027 | Base Option Design Yr 1, Construct Yr 2/4 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH11 | Corridor | Facilities | Super track head | Walking Track - Lake Howden - Upgrade | (From Track Head) Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) Upgrade at 50% of full development cost | m | 200 | 4500 | 900000 | 180000 | 162000 | 7.5% | 93150 | 6% | 2% | 6% | 186921 | 304414.2 | 1827000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
CTH12 | Corridor | Facilities | Super track head | Walking Track - Track Head to Hollyford Track | (From Track Head) Great Walks Style of Track (ref DOC estimates, cutting into virgin terrain, variable conditions and hazards) | m | 400 | 7000 | 2800000 | 560000 | 504000 | 7.5% | 289800 | 6% | 2% | 6% | 581532 | 947066.4 | 5683000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3 |  |  | Do we need to include annual DOC ongoing costs for track maintenance on existing tracks (and any other DOC functions)???
TAV3 | Te Anau | Structures | Visitor Hub | Structures - Bus Stop - Te Anau Departure | Shelter / Refuge style of development acting as a departure point for buses. Located adjacent to the Visitor Experience Hub | no. | 345000 | 1 | 345000 | 69000 | 62100 | 5% | 23805 | 6% | 2% | 6% | 69986.7 | 113978.34 | 684000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
TAV1 | Te Anau | Structures | Visitor Hub | Structures - Visitor Experience Hub - Te Anau | Facility developed to act as the focal point for the overall experience in Te Anau. Ticketing, interactive displays, information, services. | m2 | 5000 | 1000 | 5000000 | 1000000 | 900000 | 5% | 345000 | 10% | 2% | 6% | 1304100 | 1709820 | 10259000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
TAV2 | Te Anau | Structures | Visitor Hub | Landscaping - Visitor Experience Hub - Te Anau | Provison for an enhanced enviroment including paving and landscaping surrounding the Visitor Hub | m2 | 250 | 10000 | 2500000 | 500000 | 450000 | 5% | 172500 | 10% | 2% | 6% | 652050 | 854910 | 5130000
TAV4 | Te Anau | Transport | Visitor Hub | Pavements - Visitor Experience Hub - Te Anau | Parking provided for drop off and short term carparking and for Bus Transfers. Allowance for the equivalent of 60 vehicle parks | no. | 8320 | 60 | 499200 | 99840 | 89856 | 5% | 34444.8 | 6% | 2% | 6% | 101267.712 | 164921.7024 | 990000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
TAV8 | Te Anau | Transport | Visitor Hub | Carriageway - Visitor Experience Hub - Te Anau | Allowance for the realignment of roadways in the vicinity of the visitor hub and intersection upgrades for the movement of buses etc within Te Anau. Scope would require definition based on final selected location | m | 1730 | 1000 | 1730000 | 346000 | 311400 | 5% | 119370 | 6% | 2% | 6% | 350947.8 | 571543.56 | 3430000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
TAB3 | Te Anau | Transport | Access Systems | Buses - Capital Investment | Selected bus infrastructure for the conveyance of visitors to and from Piopiotahi | no. |  | 156 | [10 empty] | 141804000
| Te Anau | Transport | Access Systems | Buses - Phase 1 | Vehicles for movement from Te Anau to Piopiotahi - 50% year Zero | no. | 750000 | 78 | 58500000 | 0 | 0 | 0% | 0 | 0% | 1% | 0% | 585000 | 11817000 | 70902000 | 2 | 2024 | 0 | 2024
| Te Anau | Transport | Access Systems | Buses - Phase 2 | Vehicles for movement from Te Anau to Piopiotahi - 25% year 10 | no. | 750000 | 39 | 29250000 | 0 | 0 | 0% | 0 | 0% | 1% | 0% | 292500 | 5908500 | 35451000 | 12 | 2034 | 0 | 2034
| Te Anau | Transport | Access Systems | Buses - Phase 3 | Vehicles for movement from Te Anau to Piopiotahi - 25% year 20 | no. | 750000 | 39 | 29250000 | 0 | 0 | 0% | 0 | 0% | 1% | 0% | 292500 | 5908500 | 35451000 | 22 | 2044 | 0 | 2044
TAB1 | Te Anau | Transport | Transport Terminal | Buses - Base of Operations | Area for the operation and maintenance of buses to take visitors from Te Anau to Piopiotahi. Includes facilities for Bus driver resting, bus mainteance, charging and overnight housing | [13 empty] | 16804000
| Te Anau | Transport | Transport Terminal | Buses - Base of Operations - Parking | Housing of shuttles and buses - includes allowance for charging hubs | m2 | 259 | 14980 | 3879820 | 775964 | 698367.6 | 5% | 267707.58 | 6% | 2% | 6% | 787060.2852 | 1281783.893 | 7691000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Te Anau | Transport | Transport Terminal | Buses - Base (Generator) | Power for charging hubs - Backup generator | no. | 116840 | 0 | 0 | 0 | 0 | 5% | 0 | 6% | 2% | 6% | 0 | 0 | 0 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Te Anau | Transport | Transport Terminal | Buses - Base (Transformer) | Power for charging hubs - Transformer | no. | 125250 | 1 | 125250 | 25050 | 22545 | 5% | 8642.25 | 6% | 2% | 6% | 25408.215 | 41379.093 | 249000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Te Anau | Transport | Transport Terminal | Buses - Base of Operations - Building | Building / structure for drivers and maintenance | m2 | 3600 | 1200 | 4320000 | 864000 | 777600 | 5% | 298080 | 10% | 2% | 6% | 1126742.4 | 1477284.48 | 8864000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
TAB2 | Te Anau | Transport | Transport Terminal | Pavements - Park and Ride - Te Anau | Car Parking (Spaces) for Park and Ride. To be established adjacent to the Base of Operations for buses to make use of shared facilities, and to optimise the use of the pavement areas (peak season the bus storage area can be used for overflow parking) | no. | 8500 | 1000 | 8500000 | 1700000 | 1530000 | 5% | 586500 | 6% | 2% | 6% | 1724310 | 2808162 | 16849000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
TAV5 | Te Anau | 3 Waters | Visitor Hub | Services - Wastewater | Modification required to the wastewater systems in the vicinity of the Visitor Hub including connection costs to the Council Network | [13 empty] | 152000
| Te Anau | 3 Waters | Visitor Hub | WW - Pipelines (Hub) | Assumed connection to Council Schemes - allowance for internal infrastructure | m | 185 | 200 | 37000 | 7400 | 6660 | 5% | 2553 | 6% | 2% | 6% | 7505.82 | 12223.764 | 74000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Te Anau | 3 Waters | Visitor Hub | WW - Manholes (Hub) | Assumed connection to Council Schemes - allowance for internal infrastructure | no. | 4700 | 3 | 14100 | 2820 | 2538 | 5% | 972.9 | 6% | 2% | 6% | 2860.326 | 4658.2452 | 28000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Te Anau | 3 Waters | Visitor Hub | WW - Council Connection (Hub) | Assumed development contribution to the Council for Connection of the Hub | no. |  | 1 | [10 empty] | 50000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
TAV6 | Te Anau | 3 Waters | Visitor Hub | Services - Potable Water | Modification required to the potable water systems in the vicinity of the Visitor Hub including connection costs to the Council Network | [13 empty] | 123000
| Te Anau | 3 Waters | Visitor Hub | PW - Pipelines (Hub) | Assumed connection to Council Schemes - allowance for internal infrastructure | m | 165 | 200 | 33000 | 6600 | 5940 | 5% | 2277 | 6% | 2% | 6% | 6694.38 | 10902.276 | 66000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Te Anau | 3 Waters | Visitor Hub | PW - Council Connection (Hub) | Assumed development contribution to the Council for Connection of the Hub | no. |  | 1 | [10 empty] | 50000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
| Te Anau | 3 Waters | Visitor Hub | PW - Valves (Hub) | Assumed connection to Council Schemes - allowance for internal infrastructure | no. | 1750 | 2 | 3500 | 700 | 630 | 5% | 241.5 | 6% | 2% | 6% | 710.01 | 1156.302 | 7000 | 0 | 2022 | 3 | 2025 | Base Option Design Yr 1, Construct Yr 2/3
TAV7 | Te Anau | Facilities | Visitor Hub | Structure - Jetty | Jetty facility that would align with the Visitor Hub. Developed based on demand at location | m | 10000 | 50 | 500000 | 100000 | 90000 | 5% | 34500 | 6% | 2% | 6% | 101430 | 165186 | 992000
TAV9 | Te Anau | Facilities | Visitor Hub | Te Anau Interpretation | Budget allowance for the establishment of interpretive materials throughout Te Anau (Signage, Displays, Services, incl. within the hub) | no. |  | 1 | [10 empty] | 1000000
RELEASED BY THE MINISTER OF CONSERVATION
Note on I3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short List 7/10/2020: - GFA = 1,540m2 (25m2 per room x 50 rooms, services 150m2, 15% circulation or 140m2, (excludes commercial kitchen which is in hub). This is a 3.5 star/eco experience type facility.
Note on I4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short List 7/10/2020: - GFA = 1,540m2 (25m2 per room x 50 rooms, services 150m2, 15% circulation or 140m2, (excludes commercial kitchen which is in hub). This is a 3.5 star/eco experience type facility.
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assume 10% uplift in structural requirements to accomodate increased Safety Factor
Note on I5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short List 7/10/2020: - GFA = 1,540m2 (25m2 per room x 50 rooms, services 150m2, 15% circulation or 140m2, (excludes commercial kitchen which is in hub). This is a 3.5 star/eco experience type facility.
Note on I7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short List 7/10/2020: - - Assumes 320 residents (at peak). A combined GFA of circa a max of 6,100m2 (long and short stay/singles and couples). Important Note: bunk rooms and shared toilets would significantly lower this calculation. For example, having 100 people in a shared room could reduce the GFA by more than 1,500m2. - 15m2 per room average x 320 4,800m2, 100m2 kitchens, 385m2 dinning, social areas 200m2 service areas 40m2, 10% circulation 552.5m2 Reply: Assumed that shared accomodation model will be adopted with 6100m2 - 1000m2 used.
Note on H8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assume 10% uplift in structural requirements to accomodate increased Safety Factor
Note on I8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short List 7/10/2020: - - Assumes 320 residents (at peak). A combined GFA of circa a max of 6,100m2 (long and short stay/singles and couples). Important Note: bunk rooms and shared toilets would significantly lower this calculation. For example, having 100 people in a shared room could reduce the GFA by more than 1,500m2. - 15m2 per room average x 320 4,800m2, 100m2 kitchens, 385m2 dinning, social areas 200m2 service areas 40m2, 10% circulation 552.5m2 Reply: Assumed that shared accomodation model will be adopted with 6100m2 - 1000m2 used.
Note on H12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bishop, Shane there are two structures/parts, namely the visitor hub and marine centre in the shortlist - I think we should cost separately even if they are built into parts of same building Reply: Agreed
Note on I12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short List 7/10/2020: Estimated GFA 950m2 front of house (TBC). Size depends on approach and final hub and transport model. • Gallery 650m2 (black box high stud) – icon architecture • Audio-visual / seminar room –80m2 • Viewing room with interpretation / touch tanks (views over water, light, high stud) 200m2 • Office 20m2 • Plant room / back of house / loading dock 40m2 • Assume shared foyer, toilets and some additional back of house with visitor hub. Reply: Assessed as the footprint required for the Marine Interpretive Centre
Note on H13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Bishop, Shane there are two structures/parts, namely the visitor hub and marine centre in the shortlist - I think we should cost separately even if they are built into parts of same building
Note on I13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short List 7/10/2020: Estimated GFA 950m2 front of house (TBC). Size depends on approach and final hub and transport model. • Gallery 650m2 (black box high stud) – icon architecture • Audio-visual / seminar room –80m2 • Viewing room with interpretation / touch tanks (views over water, light, high stud) 200m2 • Office 20m2 • Plant room / back of house / loading dock 40m2 • Assume shared foyer, toilets and some additional back of house with visitor hub. Reply: Assessed as the footprint required for the Marine Interpretive Centre
Note on H14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assume 10% uplift in structural requirements to accomodate increased Safety Factor
Note on I14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short List 7/10/2020: Estimated GFA 950m2 front of house (TBC). Size depends on approach and final hub and transport model. • Gallery 650m2 (black box high stud) – icon architecture • Audio-visual / seminar room –80m2 • Viewing room with interpretation / touch tanks (views over water, light, high stud) 200m2 • Office 20m2 • Plant room / back of house / loading dock 40m2 • Assume shared foyer, toilets and some additional back of house with visitor hub. Reply: Assessed as the footprint required for the Marine Interpretive Centre
Note on I15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From the Short List, nominated as 1,800 m2
Note on I16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From the Short List, nominated as 1,800 m2
Note on H17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assume 10% uplift in structural requirements to accomodate increased Safety Factor
Note on I17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From the Short List, nominated as 1,800 m2
Note on I19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scale: Light touch – under 100m2 (links with 2.1). Administration of a public boat ramp is incorporated into the design, along with potential community facilities. or 3.4b) Enhance deep water basin commercial/ recreational wharf, including optimising boat ramp management GFA of 600m2 Allow for 350m2 Reply: Add 300m2 for operations
Note on H29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: estimate on the basis of a robust bus shelter and a toliet block
Note on I30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: realignment of the taxiway and terminal space
Note on I31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: allowance for 200 carpark spaces
Note on H32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 75% of Carriageway figure as reduced width (15m compared to 20m)
Note on I41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: assessed as 1500m2 and 80m2 per bus storage (refer to Go Bus storage depot, Chch in Te Anau TAB)
Note on I47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumes Manholes at 80m intervals on average
Note on I51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: assumes a valve or hydrant at 135m intervals
Note on I60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Approx. measure at 2400m with an addition of 50% for variance in the alignment and for structures
Note on T61: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From Craig Jones
Note on I67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Short List 7/10/2020: - Could be one open sided timber structure or separated into 3-4 dispersed or clustered modules of circa 50m2 -66m2. therefore allow for (4 * 66 + 25%) 330m2 allowed for
Note on I71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: assumes a valve or hydrant at 135m intervals
Note on I74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumes Manholes at 80m intervals on average
Note on T89: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From Craig Jones
Note on I90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: length of highway between the two locations
Note on I91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: length of highway between the two locations
Note on I92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Estimated GFA 200m2 front of house (TBC). • Audio-visual / seminar room –80m2 • Viewing room with interpretation(views over water, light, high stud) 50m2 • Office 20m2 • Entry / reception 50m2
Note on F97: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: refer Corridor Tab for information
Note on F98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: refer Corridor Tab for information
Note on F99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: refer Corridor Tab for information
Note on F100: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: refer Corridor Tab for information
Note on F102: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: refer Corridor Tab for information
Note on F103: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: refer Corridor Tab for information
Note on I106: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: compared as the size of the existing facility in Te Anau
Note on I109: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: allowance for modifications that may be required to existing roads to accomodate the vehicle fleet
Note on I110: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vingrys, Saulius Email 20/10/2020 "The bus fleet is pretty large, 156 buses in total during the peak season – 148 buses at Te Anau and 8 buses at Piopiotahi. We will also require approximately 25-30 bus parking spaces for buses that arrived to Piopiotahi and wait for the afternoon departure peak. Please see below – two scenarios plotted below showing the change in bus numbers at Te Anau and Piopiotahi throughout the day. This is an indication and can probably be further refined. There will have to be two areas at Piopiotahi and Te Anau – one for bus drop-off and pick-up and another for bus parking (overnight or for a few hours)."
Note on I111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Vingrys, Saulius Email 20/10/2020 "The bus fleet is pretty large, 156 buses in total during the peak season – 148 buses at Te Anau and 8 buses at Piopiotahi. We will also require approximately 25-30 bus parking spaces for buses that arrived to Piopiotahi and wait for the afternoon departure peak. Please see below – two scenarios plotted below showing the change in bus numbers at Te Anau and Piopiotahi throughout the day. This is an indication and can probably be further refined. There will have to be two areas at Piopiotahi and Te Anau – one for bus drop-off and pick-up and another for bus parking (overnight or for a few hours)."
Note on I115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: assessed as 2500m2 and 80m2 per bus storage (refer to Go Bus storage depot, Chch in Te Anau TAB)
Note on H119: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: allows for 20m2 per lot for land purchase
Note on I122: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assumes Manholes at 80m intervals on average
Note on I127: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: assumes a valve or hydrant at 135m intervals
Note on T129: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: From Craig Jones

## Reference Costings
Infrastructure | Description | Quantity | Unit | Raw Rate | Unit Rate | Reference
Transport | State Highway | 100 | m | 172200 | 1730 | Refer to spreadsheet from Nigel Lister: Email dated 13 October 2020 Applicable to Greenfields Rural State Highway: Assumptions: rural, no lighting, moderate to good subgrade conditions Calc includes: 2 x 0.5 m unsealed shoulder, 2 x 1.5 m sealed shoulder, 2 x 3.5 m vehicle lanes, carriageway width 11 m, subbase (AP65) depth 250 mm, basecourse M/4 AP40 depth 150 mm, two coat chip seal, standard drainage, delineation and signage, 25 % allowance for earthworks, establishment, TTM, utility services & contingency accounted for.
Transport | Shoulder widening | 100 | m | 92100 | 930 | Refer to spreadsheet from Nigel Lister: Email dated 13 October 2020 Applicable to Greenfields Rural State Highway Shoulder Widening: Assumptions: rural, no lighting, moderate to good subgrade conditions Calc includes: 2 x 0.5 m unsealed shoulder, 2 x 1.5 m sealed shoulder, subbase (AP65) depth 250 mm, basecourse M/4 AP40 depth 150 mm, two coat chip seal, standard drainage, delineation and signage, 25 % allowance for earthworks, establishment, TTM, utility services & contingency accounted for.
Transport | Shuttles |  | ea |  | 750000 | Estimate provided by Darren Davis 28/10/2020
Transport | Buses |  | ea |  | 750000 | Estimate provided by Darren Davis 28/10/2020
Transport | Parking/carpark + drainage | 20 | spaces | 166300 | 8320 | Refer to spreadsheet from Nigel Lister: Email dated 13 October 2020 Applicable to Greenfields Carpark + Surface Drainage Assumptions: rural, lighting, moderate to good subgrade conditions, CCTV. Calc includes: each car space is 2.2 m wide + 0.5 m extra width per lane circulation, subbase (AP65) depth 200 mm, basecourse M/4 AP40 depth 120 mm, 40 mm thick AC10, standard drainage, signage, 20% allowance for earthworks, establishment, TTM, utility services & contingency accounted for.
Transport | Parking/pullover | 1 | m2 | 250 | 250 | Refer to spreadsheet from Nigel Lister: Email dated 13 October 2020 Based on Greenfields Rural Shoulder Widening Calculation Assumptions: rural, no lighting, moderate to good subgrade conditions Calc includes: 1 x 0.5 m unsealed shoulder, 1 x 3 m sealed shoulder, subbase (AP65) depth 250 mm, basecourse M/4 AP40 depth 150 mm, two coat chip seal, standard drainage, delineation and signage, 25 % allowance for earthworks, establishment, TTM, utility services & contingency accounted for.
Transport | State Highway - Safety Improvements |  | m
Transport | National Park Entrance |  | ea |  | 345000 | Estimate: Assumed equivalent to a robust bus shelter
Transport | Generator and Services | 1 | ea | 116830.88 | 116840 | Refer to Pines WWTP Contract (June 2020) Assumptions: 500kVa supply required Calc includes: 500KvA generator supply and install including auto change over.
Transport | Land Redevelopment | 1 | m2 | 67.795 | 70 | Filling with imported AP65, including compaction. Assumed 500mm (on average for fill), noting that the extent of the land rebuild may extend beyond the area of interest. Based on a figure of $135.59 m3 placed and compacted
Facilities | Transformer | 1 | ea | 125249.46 | 125250 | Refer to Pines WWTP Contract (June 2020) Assumptions: 500kVa supply required Calc includes: High voltage (HV) & Transformer supply and install, plus cabling
Facilities | Landscaping - Development of landscaping areas (grassed areas or equivalent) |  | m2 |  | 119 | From Rawlinsons 2013-14 (inflated for 2020 prices *1.15): Unit rate includes: site clearance (strip 50 mm and remove from site) - $0.70 / m2 Top soil (rotary hoeing + excavate topsoil from stockpile + import topsoil and spread in layers, rake & level 150 mm) - $18.00 /m2 Allowance for estblishment of garden areas / plantings / area wide treatments - $100.00 /m2 (as per Boffa Miskell Quote) [Assumption of initial rate based on Dunedin prices] Increase to $100/m2 total based on estimates provided by Boffa Miskell 19/11/2020
Facilities | Removal of Pavement and Landscape - Development of landscaping areas (planted areas) |  | m2 |  | 131 | From Rawlinsons 2013-14 (inflated for 2020 prices *1.15): Unit rate includes: site clearance (strip 50 mm and remove from site) - $13 / m2 Top soil (rotary hoeing + excavate topsoil from stockpile + import topsoil and spread in layers, rake & level 150 mm) - $18.00 /m2 Allowance for estblishment of garden areas / plantings / area wide treatments - $100.00 /m2 (as per Boffa Miskell Quote) [Assumption of initial rate based on Dunedin prices]
Facilities | Premiere_Landscaping |  | m2 |  | 250 | Assumed, on average, to be equivalent in cost to a Paved Surface. Grassed / planted areas offset by paving and features installed.
Facilities | Metaled Pavement |  | m2 |  | 190 | as per estimates for Walking Tracks - Fully Developed but converted to a m2 basis (1.5m wide tracks)
Facilities | Walking Track - Concrete Surfacing |  | m2 |  | 200 | Based on Boffa Miskell Quote (19/11/2020)
Facilities | Land Purchase | 724680 | m2 | 3100000 | 9 | Based on Southland District Council Rates / Valuation (see attached in Te Anau TAB). Allow 100% uplift due to proximity to urban limits and submission of plan change to SDC to make use of site for this purpose. Equates to approx $85,000 / ha
Facilities | Walking Track - Fully Developed (DOC description required) | 100 | m | 27700 | 280 | Refer to spreadsheet from Nigel Lister: Email dated 13 October 2020 Applicable to Greenfields Unsealed Walking Track: Assumptions: rural, no lighting, moderate to good subgrade conditions Calc includes: track width 1.5 m, subbase (AP65) depth 150 mm, running course (AP20/crusher dust) depth 50 mm, timber edging, standard drainage, signage, 25% allowance for earthworks, establishment, TTM, utility services & contingency accounted for. | Craig to provide DOC Description
Facilities | Walking Track - Fully Developed Premier |  |  |  | 470 | Uplift for 2.5m wide track
Facilities | Walking Track - DOC Great Walks |  | m |  | 400 | From: John Twidle <jtwidle@doc.govt.nz> Sent: Thursday, 22 October 2020 8:14 AM The team here use the standard figure of $400 per metre for estimating the cost of track work (new tracks). That may sound high for some or low for others (depending on the extent of formation needed and terrain) but it works out as a very good average for all types of track (give & take).
Facilities | Cycleway - Fully Developed | 2400 | m | 1500000 | 625 | Based on Boffa Miskell Quote (19/11/2020)
Facilities | Expansion of Homer Tunnel Eastern Portal |  | ea |  | 25000000 | ESTIMATE ONLY as a placeholder - Assumed to be a rockfall structure with area for bus pull over in safe zone.
Facilities | Installation of underground power cabling | 1 | m | 168.7775 | 170 | From Kaikoura EQ repair programme, installation of main power supply (noting that additonal cost for ducting removed). Allows for: 3 phase 4 Single Core Aluminium 120mm2 Cable Supply and Install Mag Slab and Tape Install Electrical Cable in trench a Cable pit every 800m @ $3678 ea
Structures | Hotel 2-3 Star | 1 | m2 | 4600 | 4600 | Calculated from QV CostBuilder - 2020 costs [Referred to by Structures Team] Average cost per m2 for typical hotel building. Assumes flat site & good ground conditions. Figure based on: 4 - 8 storeys, basic building, reception, foyer, bedrooms, bar, restaurant, kitchen, laundry, gym, HVAC, lifts, medium standard finishes, 45 m2 per bedroom. All inclusive unit rate cost includes building, services and fit out. [Assumption of initial rate based on Dunedin pricing].Uplift of 33% to marry in with quotes provided by Boffa Miskell (19/11/2020)
Structures | Hotel 3-4 Star | 1 | m2 | 5800 | 5800 | Calculated from QV CostBuilder - 2020 costs [Referred to by Structures Team] Average cost per m2 for typical hotel building. Assumes flat site & good ground conditions. Figure based on: medium to high rise, basic building, reception, foyer, bedrooms, bars, restaurants, kitchen, service and plant facilities, HVAC, lifts, emergency generator, waste compactor, medium-standard finishes, 57 m2 per bedroom. All inclusive unit rate cost includes building services and fit out. [Assumption initial rate based on Dunedin pricing]. Uplift of 33% to marry in with quotes provided by Boffa Miskell (19/11/2020)
Structures | Motel | 1 | m2 | 3600 | 3600 | Calculated from QV CostBuilder - 2020 costs [Referred to by Structures Team] Average cost per m2 for a standard quality motel building. Assumes flat site & good ground conditions. Figure based on a standard quality motel, up to 2 storeys, basic building, office, reception, laundry decks, verandahs & services, excludes HVAC, basic standard finishes, 50 m2 per accommodation unit. All inclusive rate cost includes building, services & fit out. [Assumption initial rate based on Dunedin pricing].Uplift of 66% to marry in with quotes provided by Boffa Miskell (19/11/2020)
Structures | Visitor Centre | 1 | m2 | 5000 | 5000 | Calculated from QV CostBuilder - 2020 costs [Referred to by Structures Team] Based on average cost per m2 for a Community Centre and Library. Assumes flat site & good ground conditions. Figure based on 1 storey building, meeting rooms, office, workrooms, toilets, HVAC, fire, security, medium standard finishes. [Assumption initial rate based on Dunedin pricing]. Uplift of 66% to marry in with quotes provided by Boffa Miskell (19/11/2020) | Experience element (KATIE at $5,000/m2)
Structures | Bus Shelter - Light | 1 | ea | 34000 | 34000 | Calculated from QV CostBuilder - 2020 costs [Referred to by Structures Team] Calculated using relevant elemental components for factory/warehouse under 20 m span, colorsteel cladding. Rate assumes flat site & good ground conditions, excludes: authority fees, external works & facilities, land, demolition, utilities, professional fees. Assume bus stop area of 2.5 m x 13.5 m [33.75 m2]. [Assumption initial rate based on Auckland pricing, then inflated for Dunedin pricing]. Allow 30m2 upgrade of shoulder to accomodate at $280 / m2 | Bus Shelter - Light - Allow for waterproof stretch awning attached between poles in peak season or simple solid roof (site dependant). Allow for a single sealed vault toilet. Allow for internet /wifi / mobile connection.
Structures | Bus Shelter - Minor | 1 | ea | 164000 | 164000 | Assumed bus stop area of 2.5 m x 13.5 m [33.75 m2] but applied at a rate aligned with the Hotel Structural requirements (2-3 Star). To accommodate concrete structure, steel portal frame design. Allow 30m2 upgrade of shoulder to accomodate at $280 / m2 | Bus Shelter - Basic - Allow for timber lined structure and interpretation boards. Waterproof stretch side awning attached in peak season to increase capacity. Allow for a single sealed vault toilet. Allow for internet /wifi / mobile connection.
Structures | Bus Shelter - Robust | 1 | ea | 345000 | 345000 | Assumed bus stop area of 5 m x 15 m [75 m2] but applied at a rate aligned with the Hotel Structural requirements (2-3 Star). To accommodate concrete structure, steel portal frame design. | Bus Shelter - Robust / Key Nodes - Allow for timber lined structure and interpretation boards. Waterproof stretch side awning attached in peak season to increase capacity. Allow for two sealed vault toilets. Allow for internet /wifi / mobile connection.
Structures | Demolition | 1 | m2 |  | 140 | From Rawlinsons 2013-14 (inflated for 2020 prices *1.15): Rate for demolition of a office building, 2-storey. Rate is for a whole structure per square metre of gross floor area, based on volume of building. Cost includes demolition, including grubbing up foundations, and removing debris of office buildings (reinforced concrete floor slabs, concrete wall, metal roof). Rate assumes normal demolition periods, no site access problems and includes removal of all debris. [Assumption initial rate based on Dunedin pricing].
Structures | Viewing Platform | 161 | m2 | 201250 | 1250 | Timber and Steel Viewing platform based on Boffa Miskell Quote (19/11/2020)
Structures | Covered Walkway | 13.5 | m | 24818 | 1840 | Assumed to be aligned to the equivalent per metre rate for a typical, basic bus shelter installed. (2.5m deep and 13.5m long for $24,818
Structures | Pontoon |  | m |  | 3000 | Estimate
Structures | Wharf Structure |  | m |  | 10000 | Estimate
Structures | Retaining Wall - King Post System | 1 | m |  | 3000 | Estimate
3 Waters | Excavate, bed, supply and install PVC gravity main to depths 0 - 2.0m. Includes all labour, plant, backfilling, and reinstatement in grass. | 100 | m | 165 | 165 | Kaikoura On Site/Property works supply and install 100mm up to 1.5m depth $131.64, 150mm up to 1.5m Depth $150.52, 375mm 1.5 -2.0m deep $707.06, cost for Asbestos $54.47/m, reinstatement Asphalt $30/m
|  | 150 | m | 185 | 185
|  | 225 | m | 250 | 250
|  | 300 | m | 550 | 550
|  | 450 | m | 700 | 700
3 Waters | Excavate, bed, supply and install PE Pressure main to depths 0 - 2.0m. Includes all labour, plant, backfilling, and reinstatement in grass. | 100 | m | 165 | 165
|  | 150 | m | 185 | 185
|  | 225 | m | 250 | 250 | Use rates as stated above (majority of costs in trenching, bedding and reinstatement)
3 Waters | 1050mm manhole, installed complete with lockdown cover |  | ea | 4700 | 4700 | Kaikoura DC Reticulation Renewal Package April 2020
3 Waters | RS Gate Valve installed, including toby box |  | ea | 1750 | 1750 | Kaikoura DC Reticulation Renewal Package April 2020 ($1726 for 150mm valve installed)
3 Waters | Fire Hydrant installed, including toby box |  | ea | 4650 | 4650 | Kaikoura DC Reticulation Renewal Package April 2020 ($3104.73 for 150mm valve installed, increase by 50% to allow for range of sizes on average)
3 Waters | 1 concrete res size 500m3 | 500m3 | ea | 450000 | 450000 | From Waimea Water Supply strategy estimates. Does not include Design Fees, PM etc
3 Waters | Development of well to NZDWS | 30 | m | 36000 | 1200
3 Waters | 1 toilet block and WW Treatment system (package septic tank) |  | ea |  | 352500 | Estimate aligns with the Boffa Miskell Quote 19/11/2020
3 Waters | Vaulted Toilet (single unit) |  | ea |  | 35800 | Allowance for single vaulted toilet arrangement adjacent an additional service / facility such as a bus stop or parking area At a rate of $33,000 for the vaulted unit and 10m2 @ $280 / m2 for surrounding area surfacing
3 Waters | Package wastewater collection, treatment and disposal system (small catchment) |  | ea |  | 1189500 | Ref: Upper Selwyn Huts June 2019 Assume 30m3 per day, 5 x pressure tank installations and Isolation kits ($14,000 ea), pressure main 700m @ $135/m, AdvanTex AX400 $350,000, land based disposal @ 15000m2 assumed and $45/m2 established.
3 Waters | Package wastewater collection, treatment and disposal system (small-medium catchment) |  | ea |  | 1052500 | Ref: Upper Selwyn Huts June 2019 Assume 60m3 per day, 5 x pressure tank installations and Isolation kits ($14,000 ea), pressure main 700m @ $135/m, AdvanTex AX700 $700,000, land based disposal @ 12000m2 assumed and $15/m2 established.
3 Waters | Package treatment and disposal system (small-medium catchment) |  | ea |  | 790000 | Ref: Upper Selwyn Huts June 2019 Assume AdvanTex AX700 $700,000, land based disposal @ 12000m2 assumed and $15/m2 established.
3 Waters | Package potable water treatment system (small catchment) |  | ea |  | 650000 | Potable water treatment simple intake + pipelines +UV
Power | Package Turbine and Generator for power generation, installed |  | ea |  | 1100000 | Ref: Sumbitted quote for from Vortex Hydro (November 2020) Turbine Hydro 300kW + 500kW Generator Hydro 330kVA + 550kVA PLC governor control system Low voltage (415V) switchgear panel 24VDC panel ACDB / HPU / MIV Transformer 415V/11kV Installation, Commissioning and Training for both stations
RELEASED BY THE MINISTER OF CONSERVATION
Note on E42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Typical Figure for WW Grav.
Note on E43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Typical Figure for SW Grav. (increased size to WW and Conc. rather than PVC)

## Assumptions
Item | Description
1 | if the infrastructure doesn’t change then OPEX stays the same and therefore excluded
2 | Insurance of structures (OPEX) excluded
3 | Base Rates are built up, where applicable, from documented rates for Dunedin (municipal area), with uplift applied for location
4 | Exclude land purchase costs with all options / activities within the Fiordland National park
5 | No costs included for Manapouri
6 | No costs included for Patea / Doubtful Sound - assume operators will be able to apply some of the Piopiotahi lessons/principles including improving evacuation pathways and protocols, etc
7 | Configuration for complete works as per TABs for Piopiotahi, Corridor and Te Anau contained in this document
8 | Power and Potable water provisions (supply) for Knobs Flat assumed to be sufficient for the revised facilities
9 | For BAU, renewal of the Aerodrome Runway and Wastewater Treatment / network is required to align with deterioration and consenting respectively. Climate change / relocation of structures is not addressed, nor is renewal of existing structures.
10 | Design for Structures are applied at 10% for balance of infrastructure a figure of 6% is used
RELEASED BY THE MINISTER OF CONSERVATION

## Piopiotahi_30112020
Preferred Option
For Demolition
|  | Hub | 6125 | 19 dwelling at approx 150m/2 each
|  | Terminal | 1300 | 4900 footprint, 25% extra for two levels
|  | Accommodation | 2850
| 6 locations of "Bunkers" |  |  |  | 3700 m2
- 4 on the walkways/marshlands
- 2 adjacent to areas where people will accumulate outside of built structures/buildings
RELEASED BY THE MINISTER OF CONSERVATION

## Corridor_30112020
|  |  |  | 20% | additional for vertical distance and fitting in with landscape
|  |  |  | 6200 | m | 5100 | Lake Marian Loop
|  |  |  | 4600 | m | 3800 | Waterfall Loop
|  |  |  | 2300 | m | 1900 | Nature Loop
|  |  |  | 2700 | m | 2200 | Key Summit Link
|  |  |  | 4500 | m | 3700 | Lake Howden (single way)
|  |  |  | 3600 | m2 |  | Super Track Head (basis Castle Hill Parking area)
|  |  |  | 12900 | m | 10700 | Key Summit Link (from Cascade Creek)
Note: current Lake Marian Track is 3100m
|  |  |  | 7000 | m |  | from Lake Marian carpark to Hollyford Camp
[8 empty] | Knobs Flat Walks | KF1 | 1000 | abled
[9 empty] | KF2 | 1000 | wheelchair
[9 empty] | KF3 | 1400 | abled
Hop on / off | Piopiotahi | Hub | Piopiotahi
| Interim | Basic Bus Stop | Corridor
| Interim | Basic Bus Stop | Corridor
| Homer Tunnel | Loop 2 - West | Corridor
| Homer Tunnel | Portal - East | Corridor
| Lake Marian | Car Park Upgrade | Corridor
| Divide | Basic Bus Stop | Corridor
| Knobs Flat | Robust Bus Stop | Corridor
| Interim | Basic Bus Stop | Corridor
| Eglinton Reveal | Robust Bus Stop | Corridor
| FNP Entry | Robust Bus Stop | Corridor
| Interim | Basic Bus Stop | Corridor
| Interim | Basic Bus Stop | Corridor
| Te Anau | Hub | Te Anau

## Te Anau_30112020
Connecting infrastructure
Cycle and walkways (connecting with the Lake2Lake trail)
Shuttle services
60 buses housed in approx 5000m2
4000 m2 hard standing for access
900 m2 for service building / maintenance